## MRF
MATERIAL REQUISITION FORM
SITE DETAILS |  | Type Of Service: | MATERIAL ONLY/OWN COLLECTION
|  | Mode of Transport: | LORRY
|  | Project: | HAMMER18
|  | Project Naming Convention: | PO5 CUQ1 H1B1
|  | Region: | SARAWAK
|  | Site Name : | SGPINANGKCH
|  | Location ID: | Q00068
|  | Network No: | 96049041
|  | WBS No: | ECM11.100111.20001
PICK UP DETAILS |  |  | PAN ASIA LOGISTICS MALAYSIA SDN BHD, RT CARGO WAREHOUSE, LOT 1197, JALAN BAKO, 93450 KUCHING, SARAWAK
Pick Up Point Address:
|  | Contact Person : | SZE KIAT - 0168869579
Delivery Details
|  | Contact Person At Site: | IEZZPRO
|  | Target Collection/Delivery Date: | 2019-01-09
|  | Required Arrival Date at site: | ETA
E/// PO NO. | CASE NO. | PRODUCT CODE | PRODUCT DESCRIPTION | QTY | UOM | SERIAL NO. | PROJECT OWNER | NW# | REMARKS | ECM11.100032 | 2017 MY NES Celcom Hammer Cap Exp SS Sab
[10 empty] | ECM11.100045 | 2017 MY Celcom NES - Hammer Refarming EM June
|  |  | PO5 CUQ1 H1B1 IEZZPRO SARAWAK 09-01-2019 Q00068 SGPINANGKCH | [6 empty] | ECM11.100046 | 2017 MY Celcom NES - Hammer Refarming EM July
[10 empty] | ECM11.100052 | 2017 MY Celcom NES - Hammer Clawback EM
4517335798 |  | RPM77701/01000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH | ECM11.100057 | 2017 MY NES Celcom - Hammer Clawback EM
4517335798 |  | RNT44732/02 | CONNECTOR/Circular Power cable connector | 3 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH | ECM11.100062 | 2017 MY NES Celcom - Hammer BP EM
4517335798 |  | NTM1012589/1 | SET OF MATERIALS/6601 subrack kit v2,-48 | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH | ECM11.100063 | 2017 MY NES Celcom - Hammer RDO EM
4517335798 |  | RPM777291/02000 | CABLE WITH CONNECTOR/EARTH CABLE | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH | ECM11.100065 | 2017 MY NRO Celcom BP Ph2 EM
4517335798 |  | KDU137925/41 | PROCESSOR UNIT/Baseband 5212; Digital Un | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH | ECM11.100067 | 2017 MY NRO Celcom Cap Upg Q1 EM
4517335798 |  | KRC161619/1 | TRANSCEIVER/Radio 2219 B3;Radio Unit | 3 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | RPM777193/00200 | CABLE WITH CONNECTOR/DC POWER CABLE | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | SXA1342193/2 | MECHANICAL COMPONENT/Dummy 31 (Plastic v | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | SXK111539/1 | MOUNTING SET/RACK SCREW KIT | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | RPM919619/10000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | RDH10265/2 | OPTICAL TRANSCEIVER/SFP+ SM 10.3Gb/s 1.4 | 6 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | NTM2014090/2 | SET OF MATERIALS/External Alarm Interfac | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | TPM1010027/15M | CABLE/TFL 252015/16 15m SPOOLED | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | SEF901304/1 | BRACKET/RAIL BRACKET | 3 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | SEF901305/0180 | BRACKET/RAIL | 3 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | SXK1252540/1 | ASSEMBLED PARTS/MOUNTING KIT | 3 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
4517335798 |  | RPM777291/02000 | CABLE WITH CONNECTOR/EARTH CABLE | 1 | PCS |  | ECM11.100111.20001 | 96049041 | Q00068 SGPINANGKCH
|  | RPM2531610/100M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | 1 | PCS
|  | RPM2530292/20M | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU | 2 | PCS
|  | ECM-LC08-475-3000 | 4.3-10 male to DIN male, 3 meters 1/2ö superflexi jumper | 6 | PCS |  | ECM11.100111 | 96049041
|  | TFL492325/300M | POWER CABLE/2x10 mm2;UL;LSOH;Alu+Cu-scre | 100m x 3 | MTR |  | ECM11.100111 | 96049041
|  | ECM-LTTBABS2838 | Fiber Overlength box | 1 | EA |  | ECM11.100111 | 96049041
Comments:
|  |  |  | Requested by: |  | AHMADZAKI
|  |  |  | Request Date: |  | 2019-01-07
DORIETHIA PIDILIS - 011 1050 6288 |  | FSO
SZE KIAT - 0168869579 |  | IEZZPRO
FAIRUZ - 018 258 7505 / VALLA - 014 627 6718 |  | TELECORE
HOMKIM
SELECT |  | SPAC
MATERIAL & DELIVERY/DISMANTLE |  | DATASCO
TRANSPORT SERVICES ONLY |  | DANCOM
MATERIAL ONLY/OWN COLLECTION |  | DDESA
ASP SELF COLLECTION |  | NERA
MATERIALS RESERVATIONS |  | RESPONTRADE
RETURN MATERIAL |  | SEATELCO
SELECT
AIR FREIGHT
SEA FREIGHT
TRUCK
COURIER
LORRY
PAN ASIA LOGISTICS MALAYSIA SDN BHD, RT CARGO WAREHOUSE, LOT 8- INDUSTRIAL ZONE 7, KKIP, SABAH
PAN ASIA LOGISTICS MALAYSIA SDN BHD, RT CARGO WAREHOUSE, LOT 1197, JALAN BAKO, 93450 KUCHING, SARAWAK
PAN ASIA LOGISTICS MALAYSIA SDN. BHD. MAPLETREE LOGISTICS HUB - SHAH ALAM (MLHSA). LOT NO 3, PERSIARAN JUBLI PERAK, SEKSYEN 22, 40300 SHAH ALAM, SELANGOR DARUL EHSAN
SELECT
CENTRAL
EASTERN
SABAH
SARAWAK
SELECT | SELECT
BAU | PO2 RDO
HAMMER17 | PO3 REFARMING
HAMMER18 | PO3 REFARMING NEW NEW
IBC | PO4 CLAWBACK15
CELCOM | PO5 BP77
PO6 BP710
PO7 CU Q1
PO8 CU Q4
PO9 CA17
PO10 CU Q2 P1
PO11 BP117
PO12 CU Q2 P2
PO13 BP264
PO14 CB16
PO15
PO16 CUQ3
PO1 REFARM56
PO2 LTE MAX
PO3 BP2018
PO5 CUQ1 H1B1
PO6 BP38
PO7 CUH1B2
PO8 CU H2B1
LTE ACCELERATED
IBC
CELCOM
MODERNIZED
CA OKV

## SUPPORT MATERIAL
CU Q1 | ECM-0709EWEW65XX02 | Triband L900/H1800/2100/2600 65░18dBi | 3 | EA | TB LHH
| RASO-ANT-0020 | XXPol,806-960/1710-2690 MHz,Dual-Band | 3 | EA | DB LH
| RASO-ANT-0017 | XXPol,2 x 1710-2690 MHz Dual Ultra-WB | 3 | EA | DB HH
| RASO-ANT-0021 | XXXPol,3x1710-2690 MHz Triple Ultra-WB | 3 | EA | TB HHH
CA2017 | ECM-ODI4-065R18J-G | QB HHHH | 3 | EA | COMBA QB HHHH
| RASO-ANT-0016 | XXPol,790-960/790-960 MHz,Ultra-wideband | 3 | EA | DB HH
| RASO-ANT-0014 | XXXXPol,2x(694-960)/2x(1710-2690)MHz,QB | 3 | EA | QB LLHH
| ECM-ODI4-065R18J-G | QB,Xp,4x1710-2690MHz,65,17.8/17.3 dBi,RE | 3 | EA | QB HHHH
| RASO-ANT-0015 | XXXXPol,694-960/3x(1710-2690)MHz,QB | 3 | EA | QB LHHH
RDO | RASO-ANT-0024 | Outdoor Directional QB Antenna-RCU | 3 | EA | QB LHHH
| RASO-ANT-0055 | QBXpol 698-960+1710-2690 65 16.7/17.9 | 3 |  | QB LHHH
| RASO-ANT-0023 | XXXXXPol,2x(694-960)/3x(1710-2690)MHz,PB | 3 | EA | PB LLHHH
| RASO-ANT-0025 | Outdoor Directional PB Antenna-RCU | 3 | EA | PB LHHHH
CA2017 | RASO-ANT-0058 | PENTABAND LHHHH | 3 | EA | COMBA PB LHHHH
| ECM-ANTBRKT3MT | antenna bracket-2 flexi arm(76mmx3m)boom | 3 | SET
| RASO-ANT-0011 | RET Cable 3m | 3 | PCS
| ECM-LC08-475-3000 | 4.3-10 male to DIN male, 3 meters 1/2ö superflexi jumper | 6 | PCS | JUMPER FOR RRU 2217 / 2217
| ECM-LC081133000 | JUMPER DIN MALE DIN MALE - 3 meters | 12 | PCS | JUMPER COMMON
| RASO-ANT-0059 | COMBA RET CABLE 3m | 3 | PCS | COMBA RET
| RASO-ANT-0012 | RET Cable 5m | 3 | PCS | COMBA RET
| ECM-SL078RALPE | Feeder Cable 7/8" Aluminium |  | M | 7/8"
| ECM-60K1CAC05B1 | CONNECTOR 7-16 DIN (F) FOR 7/8" CABLE |  | PCS
| ECM-SLGK004C05060 | Grounding Kit for 7/8" feeder cable |  | PCS
| ECM-SL158RAPE | Feeder Cable 1 5/8" Aluminium |  | M | 1 5/8"
| ECM-60K1D7C07B1 | 7/16 Connector (F)1 5/8"Aluminium feeder |  | PCS
| ECM-SLGK004C07060 | Grounding Kit for 1 5/8" feeder cable |  | PCS
| ECM-SL012SPE | Feeder 1/2" Cable Superflex |  | MTR | 1/2"
| ECM-60S1C7C08N1 | CONN 7-16 DIN(M) STRGT FR 1/2" SuperFlex |  | PCS
| ECM-64S1C7-C08N1 | 4.3-10 male for 1/2� superflexi (Straight plug) |  | PCS
| TFL492325/300M | POWER CABLE/2x10 mm2;UL;LSOH;Alu+Cu-scre | 70m x 6 | MTR | POWER CABLE
| ECM-LTTBABS2838 | Fiber Overlength box | 2 | EA | FOB
| ECM-ESR4856ABS | Rectifier 2.7kW ESR48/56A B-S | 1 | PCS | RECTIFIER MODULE
| ECM-DD300R-05A-B-S | DCDU | 1 | PCS | DCDU
| ECM-ESAA150ACB010 | INDOOR RECTIFIER 2.9 kWa | 1 | SET | INDOOR RECTIFIER
| ECM-0991253228 | 12V AGM 150AH battery | 8 | PCS
| ECM-ESOA300ACB010 | Outdoor power system - 2900W-ESOA300ACBD | 1 | SET | SBOC 2.9kWA
| ECM-ESOA300BCBD01 | SINGLEBAY BOC 2.3 kWa | 1 | SET | SBOC 2.3kWA
| ECM-CGT12-125X | 12V GEL 125AH Battery | 8 | PCS | 2 BANK
| ECM-0991253228 | 12V AGM 150AH battery | 8 | PCS | BATT 150AH 2 BANK
| SXK1250245/1 | ASSEMBLED PARTS/MOUNTING KIT (MK mast br | 8 | PCS | RRU13/32 BRACKET
| SXK1252540/1 | ASSEMBLED PARTS/MOUNTING KIT | 8 | PCS | RRU2217/2219 BRACKET
| RPM2533512/10M | 2F LC-LC SM | 1 | PCS | ADDITIONAL
| RDH10265/2 | OPTICAL TRANSCEIVER/SFP+ SM 10.3Gb/s 1.4 | 2 | EA | ADDITIONAL
OIL 100M | RPM2531610/100M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | 1 | EA
CASCADE 10M | RPM2533512/10M | 2F LC-LC SM | 1 | PCS
CASCADE 20M | RPM2530292/20M | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU | 2 | PCS
OIL 100M | RASO-IMT-9025 | OIL CABLE 100m | 1 | PCS
CASCADE 20M | ECM-L98B-906-20000 | CASCADE CABLE 20m | 2 | PCS
2217 DC CONNECTOR | RNY10487/1 | ACCESSORIES/Connector | 1 | EA
2217/2219 DC CONNECTOR | RNT44732/02R1B | CONNECTOR/Circular Power cable connector | 1 | EA
6601+5212 | 20/BFL901009/777 | EQUIPPED CABINET/RBS 6601 ASO | 1 | EA
6601+5212 | 20/BFL901009/821 | EQUIPPED CABINET/RBS 6601 ASO | 1 | EA
6601+5216 | 20/BFL901009/819 | EQUIPPED CABINET/RBS 6601 ASO | 1 | EA
RBS6601+5216 NEW | 20/BFL901009/1728 | EQUIPPED CABINET/RBS 6601 ASO | 1 | EA
RBS6601+5212 NEW | 20/BFL901009/1732 | EQUIPPED CABINET/RBS 6601 ASO | 1 | EA
RBS 6601 SUBRACK | NTM1012589/1 | SET OF MATERIALS/6601 subrack kit v2,-48 | 1 | EA
BB5212 | KDU137925/31 | PROCESSOR UNIT/Baseband 5216; Digital Un | 1 | EA
BB5216 | KDU137925/41 | PROCESSOR UNIT/Baseband 5212; Digital Un | 1 | EA

## MASTER CHECKLIST 3JAN2019
CLASS | DETAILS | PRODUCT CODE | DESCRIPTION | SA | SB | SK | TOTAL
ANT | DB LL | RASO-ANT-0016 | XXPol,790-960/790-960 MHz,Ultra-wideband | N/A | N/A | N/A | N/A
| DB LH | RASO-ANT-0020 | XXPol,806-960/1710-2690 MHz,Dual-Band | N/A | N/A | N/A | N/A
| DB HH | RASO-ANT-0017 | XXPol,2 x 1710-2690 MHz Dual Ultra-WB | 0 | 21 | 0 | 21
| TB LHH | ECM-0709EWEW65XX02 | Triband L900/H1800/2100/2600 65░18dBi | 1 | 0 | 0 | 1
| TB HHH | RASO-ANT-0021 | XXXPol,3x1710-2690 MHz Triple Ultra-WB | 0 | 13 | 8 | 21
| QB LLHH | RASO-ANT-0014 | XXXXPol,2x(694-960)/2x(1710-2690)MHz,QB | 125 | 14 | 14 | 153
| QB LHHH | RASO-ANT-0015 | XXXXPol,694-960/3x(1710-2690)MHz,QB | 0 | 0 | 18 | 18
| QB LHHH | RASO-ANT-0024 | Outdoor Directional QB Antenna-RCU | 0 | 0 | 13 | 13
| QB LHHH | RASO-ANT-0055 | QBXpol 698-960+1710-2690 65 16.7/17.9 | 1 | 0 | 0 | 1
| QB HHHH | ECM-ODI4-065R18J-G | QB,Xp,4x1710-2690MHz,65,17.8/17.3 dBi,RE | 0 | 0 | 6 | 6
| COMBA QB HHHH | ECM-ODI4-065R18J-G | QB HHHH | 0 | 0 | 6 | 6
| PB LLHHH | RASO-ANT-0023 | XXXXXPol,2x(694-960)/3x(1710-2690)MHz,PB | 49 | 42 | 44 | 135
| PB LHHHH | RASO-ANT-0025 | Outdoor Directional PB Antenna-RCU | N/A | N/A | N/A | N/A
| PB LHHHH | ECM-G7W8W8W8W8X65V | Penta-Band 5XPol, 694-960/4X1710-2690 MH | 0 | 1 | 0 | 1
| PB LHHHH | ODI-065R16M17JJJJG | SMALL PENTABAND LHHHH- | N/A | N/A | N/A | N/A
| NEW PB LHHHH | ODI065R16M17JJJJGQ | Outdoor Directional Penta-band Antenna
| COMBA PB LHHHH | RASO-ANT-0058 | PENTABAND LHHHH | 0 | 14 | 23 | 37
ANT SUPPORT | BOOM BRACKET | ECM-ANTBRKT3MT | antenna bracket-2 flexi arm(76mmx3m)boom | 323 | 112 | 107 | 542
| RET | RASO-ANT-0011 | RET Cable 3m | 213 | 140 | 76 | 429
| RET | RASO-ANT-0012 | RET Cable 5m | 101 | 2 | 0 | 103
| COMBA RET | RASO-ANT-0059 | COMBA RET CABLE 3m | 20 | 7 | 0 | 27
JUMPER | JUMPER RRU 2219-17 / 4415 | ECM-LC08-475-3000 | 4.3-10 male to DIN male, 3 meters 1/2ö superflexi jumper | 1346 | 410 | 573 | 2329
| JUMPER 4.3-10 TO 4.3-10 | LC08-C495-3000 | 4.3-10 MALE / 4.3-10 MALE JUMPER 3m
| JUMPER COMMON | ECM-LC081133000 | JUMPER DIN MALE DIN MALE - 3 meters | 3378 | 523 | 267 | 4168
| JUMPER RRU 2219-17 / 4415 | ECM-LC08-475-5000 | 4.3-10 male-DINmale,5M 1/2â€™ SFLEX jumper | 0 | 0 | 18 | 18
7/8" FEEDER | 7/8" FEEDER | ECM-SL078RALPE | Feeder Cable 7/8" Aluminium | 96 | 227 | 100 | 423
| 7/8" CONNECTOR | ECM-60K1CAC05B1 | CONNECTOR 7-16 DIN (F) FOR 7/8" CABLE | 2736 | 23 | 130 | 2889
| 7/8" GROUNDING KIT | ECM-SLGK004C05060 | Grounding Kit for 7/8" feeder cable | 1286 | 49 | 130 | 1465
1 5/8" FEEDER | 1 5/8" FEEDER | ECM-SL158RAPE | Feeder Cable 1 5/8" Aluminium | 324 | 3050 | 3056 | 6430
| 1 5/8" CONNECTOR | ECM-60K1D7C07B1 | 7/16 Connector (F)1 5/8"Aluminium feeder | 0 | 56 | 38 | 94
| 1 5/8" CONNECTOR | ECM-60K1C7C07B1 | 7/16 Connector (F) for 1 5/8" feeder | N/A | N/A | N/A | N/A
| 1 5/8" GROUNDINGKIT | ECM-SLGK004C07060 | Grounding Kit for 1 5/8" feeder cable | 43 | 0 | 221 | 264
1/2" FEEDER | 1/2" FEEDER | ECM-SL012SPE | Feeder 1/2" Cable Superflex | 0 | 425 | 374 | 799
| 1/2" CONNECTOR 7/16 | ECM-60S1C7C08N1 | CONN 7-16 DIN(M) STRGT FR 1/2" SuperFlex | 1368 | 973 | 322 | 2663
| 1/2" CONNECTOR 4.3-10 | ECM-64S1C7-C08N1 | 4.3-10 male for 1/2� superflexi (Straight plug) | 0 | 310 | 94 | 404
DC CABLE | DC CABLE 10mm | TFL492325/300M | POWER CABLE/2x10 mm2;UL;LSOH;Alu+Cu-scre | 100003 | 13189 | 5972 | 119164
| DC CABLE 10mm | TFL492325/100M | POWER CABLE/2x10 mm2;UL;LSOH;Alu+Cu-scre | 0 | 200 | 0 | 200
| DC CABLE 6mm | TFL492324/500M | POWER CABLE/2x6 mm2;UL;LSOH;Alu+Cu-scree | 428 | 161 | 0 | 589
POWER SYSTEM | RECTIFIER MODULE | ECM-ESR4856ABS | Rectifier 2.7kW ESR48/56A B-S | N/A | N/A | N/A | N/A
| DCDU | ECM-DD300R-05A-B-S | DCDU | 0 | 5 | 7 | 12
| INDOOR RECTIFIER | ECM-ESAA150ABB01 | Indoor Rack | N/A | N/A | N/A | N/A
|  | ECM-ESAA150ABB04 | Indoor Micro (Celcom LTE) | N/A | N/A | N/A | N/A
|  | ECM-ESAA150ACB010 | INDOOR RECTIFIER 2.9 kWa | 2 | 0 | 0 | 2
|  | ECM-ESAA150BCBA01 | Indoor power system- 2300W - ESAA150BCBA | 4 | 5 | 3 | 12
| SBOC 2.9W | ECM-ESOA300ACB010 | Outdoor power system - 2900W-ESOA300ACBD | 7 | 1 | 0 | 8
| SBOC 2.3W | ECM-ESOA300BCBD01 | SINGLEBAY BOC 2.3 kWa | 0 | 8 | 0 | 8
| BATT 125AH 2 BANK | ECM-CGT12-125X | 12V GEL 125AH Battery | 49 | 0 | 0 | 49
| BATT 150AH 2 BANK | ECM-0991253228 | 12V AGM 150AH battery | 275 | 166 | 40 | 481
SYNC CABLE | SFP MODULE 2.5G | RDH10247/2 | OPTICAL TRANSCEIVER/SFP CPRI & 1000BASE- | 122 | 117 | 2 | 241
| SFP MODULE 10G | RDH10265/2 | OPTICAL TRANSCEIVER/SFP+ SM 10.3Gb/s 1.4 | 810 | 609 | 834 | 2253
| CASCADE 10M | RPM2533512/10M | 2F LC-LC SM | 30 | 64 | 60 | 154
OIL & CASCADE | OIL 100M | RPM2531610/100M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | 321 | 225 | 41 | 587
| OIL 100M | RASO-IMT-9025 | OIL CABLE 100m | 0 | 1 | 0 | 1
| OIL 100M | ECM-L98B755100M | OIL cable 100m (RPM 253 3577) | 128 | 9 | 0 | 137
| OIL 100M | RPM2533512/100M | CABLE WITH CONNECTOR/2F LC-LC SM | 16 | 69 | 0 | 85
| NEW OIL 100M | 85005597 | H&S Optic Cable 100M RPM 253 1610 | 466 |  | 320 | N/A
| OIL 50M | RPM2533512/50M | CABLE WITH CONNECTOR/2F LC-LC SM | 4 | 19 | 6 | 29
| OIL 150M | RPM2531610/150M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | N/A | N/A | N/A | N/A
| OIL 200M | RPM2531610/200M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | N/A | N/A | N/A | N/A
| OIL 150M | RASO-IMT-9027 | OIL cable, single mode, LCD - LCD RFE, 150m | 8 | 9 | 1 | 18
| OIL 300M | RASO-IMT-9033 | OILcable,singlemode,LCD-LCDRFE,300m | 2 | 0 | 0 | 2
| CASCADE 100M | RPM2530292/100M | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU | 0 | 65 | 143 | 208
| CASCADE 20M | RPM2530292/20M | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU | 21 | 136 | 45 | 202
| NEW CASCADE 20M | 85006586 | OPTICAL FIBER CBL SM LCD FXS-LCD FXS 20M | 569 | 0 | 349 | 918
| CASCADE 20M | ECM-L98B-906-20000 | CASCADE CABLE 20m | 0 | 2 | 0 | 2
FOB | FOB | ECM-LTTBABS2838 | Fiber Overlength box | 711 | 610 | 553 | 1874
RRU DC CONNECTOR | 2217 DC CONNECTOR | RNY10487/1 | ACCESSORIES/Connector | 663 | 91 | 39 | 793
| 2217/2219 DC CONNECTOR | RNT44732/02 | CONNECTOR/Circular Power cable connector | 861 | 455 | 133 | 1449
BASEBAND & RBS CONFIG | 6601+5212 | 20/BFL901009/777 | EQUIPPED CABINET/RBS 6601 ASO | 0 | 8 | 1 | 9
| 6601+5212 | 20/BFL901009/821 | EQUIPPED CABINET/RBS 6601 ASO | N/A | N/A | N/A | N/A
| 6601+5216 | 20/BFL901009/819 | EQUIPPED CABINET/RBS 6601 ASO | 0 | 0 | 11 | 11
| RBS6601+5216 NEW | 20/BFL901009/1728 | EQUIPPED CABINET/RBS 6601 ASO | 0 | 30 | 11 | 41
| RBS6601+5212 NEW | 20/BFL901009/1732 | EQUIPPED CABINET/RBS 6601 ASO | 0 | 3 | 0 | 3
| BB 5216 | KDU137925/31 | PROCESSOR UNIT/Baseband 5216; Digital Un | 9 | 10 | 3 | 22
| BB5212 | KDU137925/41 | PROCESSOR UNIT/Baseband 5212; Digital Un | 112 | 53 | 46 | 211
|  | KDU137949/1 | PROCESSOR UNIT/Baseband R503; Auxiliary | 2 |  |  | 2
| RBS6601 SUB-RACK | NTM1012589/1 | SET OF MATERIALS/6601 subrack kit v2,-48 | 197 | 107 | 51 | 355
RRU | RRU B7 | KRC161428/1 | TRANSCEIVER/Radio 2217 B7;Radio Unit | 43 | 18 | 16 | 77
|  | KRC161495/1 | TRANSCEIVER/Radio 4415 B7 | 15 | 6 | 10 | 31
|  | KRC161473/2 | TRANSCEIVER/RRUS 13 B7;Radio Unit, Type | 2 | 0 | 0 | 2
| RRU B8 | KRC161548/1 | TRANSCEIVER/Radio 2217 B8;Radio Unit | 0 | 0 | 26 | 26
|  | KRC161670/1 | TRANSCEIVER/Radio 2219 B8;Radio Unit | 30 | 111 | 25 | 166
|  | KRC161262/2 | TRANSCEIVER/RRUS 12 B8;Radio Unit, Type | 2 | 0 | 0 | 2
| RRU B1 | KRC161622/1 | TRANSCEIVER/Radio 2219 B1;Radio Unit | 62 | 4 | 8 | 74
|  | KRC161490/1 | TRANSCEIVER/Radio 2217 B1;Radio Unit | N/A | N/A | N/A | N/A
|  | KRC161466/2 | TRANSCEIVER/RRUS 13 B1;Radio Unit, Type | 9 | 32 | 0 | 41
| RRU B3 | KRC161619/1 | TRANSCEIVER/Radio 2219 B3;Radio Unit | 60 | 95 | 93 | 248
|  | KRC161637/1 | TRANSCEIVER/Radio 4415 B3;Radio Unit | 120 | 46 | 7 | 173
|  | KRC161413/1 | TRANSCEIVER/RRUS 32 B3;Radio Unit | N/A | N/A | N/A | N/A
|  | KRC161469/2 | TRANSCEIVER/RRUS 13 B3;Radio Unit | 12 | 6 | 1 | 19
RRU BRACKET | RRU13/32 BRACKET | SXK1250245/1 | ASSEMBLED PARTS/MOUNTING KIT (MK mast br | 39 | 24 | 62 | 125
| RRU2217-19/4415 BRACKET | SXK1252540/1 | ASSEMBLED PARTS/MOUNTING KIT | 256 | 336 | 291 | 883
QUADPLEXER | QUAD-DIPLEXER | KRF102301/10 | FILTER UNIT/Diplex 698-2200+B7/B41 (8-4) | 43 | 0 | 1 | 44
| QUADPLEXER | E15V90P3201 | QUADPLEXER LHHH | 0 | 3 | 0 | 3
| NEW QUADPLEXER | ECM-CB-4-GDWEDF08G | Quadplexer with DC bypass | 78 | 33 | 7 | 118
| DUMMY LOAD 100W | ECM-L-100-DM | Termination Load,100W,Din male connector | N/A | N/A | N/A | N/A
| HYBRID COUPLER | ECM-HM-3-7F-DF-02 | 698-2700MHz, 3dB Hybrid | 2 | 0 | 0 | 2
| RMU FOR 2217/2219/4415 | KRC115108/1 | TRANSCEIVER/RMU 4.3-10 Int Cables | 42 | 0 | 0 | 42
| RIU | KRC115032/2 | TRANSCEIVER/RIU (RET Interface Unit) | 104 | 20 | 2 | 126

## SOH 3 JAN2019
|  | SA | SB | SK | Total Sum of Qty Available
1/BFL901009/4 | EQUIPPED MAGAZINE/SUP 6601; Equipped mag |  | 2 |  | 2
1/KEP813102 | SWITCHING EQUIPMENT/AC meter 3-ph | 8 |  |  | 8
1/NSD20103/50 | FOUNDATION/FOUNDATION/BYB 501 | 2 |  |  | 2
10/FAB1021180/2 | SALES OBJECT/Evo C 8200 R2.0 Equipped Ca |  | 1 |  | 1
11/BYB501180 | SIDE PLATE/Side plate BYB501 H=1800 |  | 1 |  | 1
11/FAB1021180/2 | SALES OBJECT/Evo C 8200 R2.0 Equipped Su | 1 |  |  | 1
20/BFL901009/1728 | EQUIPPED CABINET/RBS 6601;ASO |  | 30 | 11 | 41
20/BFL901009/1732 | EQUIPPED CABINET/RBS 6601 ASO |  | 3 |  | 3
20/BFL901009/485 | EQUIPPED CABINET/RBS 6601;ASO |  | 1 |  | 1
20/BFL901009/760 | EQUIPPED CABINET/RBS 6601;ASO |  | 1 |  | 1
20/BFL901009/777 | EQUIPPED CABINET/RBS 6601;ASO |  | 8 | 1 | 9
20/BFL901009/819 | EQUIPPED CABINET/RBS 6601 ASO |  |  | 11 | 11
303/BFM901290 | EQUIPPED CABINET/RBS 6201;AGO |  |  | 4 | 4
305/BFL901009 | EQUIPPED CABINET/RBS 6601;AGO | 3 | 9 | 4 | 16
38/BYB501180/1 | BACK COVER/Back cover perforated 400mm | 1 | 1 |  | 2
39/BYB501/1 | END COVER2/Air guide set for top of BYB | 3 | 1 |  | 4
469760A.102 | 10009674 - ANT : RET MOTOR (469760A) - ANDREW |  |  | 4 | 4
469790A.103 | 10009680 - NSN : CABLE 3M (469790A) |  |  | 10 | 10
469870A.105 | 10009436 - SMART BIAS T KIT |  |  | 7 | 7
6/KEP813102 | SWITCHING EQUIPMENT/General purpose rela | 17 |  |  | 17
78/SBA121060/0160 | SCREW/SCREW MRT-LME M 6X16 ST FZB | 14 |  |  | 14
85005597 | H&S Optic Cable 100M RPM 253 1610 | 466 |  | 320 | 786
85006586 | OPTICAL FIBER CBL SM LCD FXS-LCD FXS 20M | 569 |  | 349 | 918
ATM200-A20 | ATM200-002 FACTORY-SET TO AISG 2.0 |  | 3 |  | 3
BAY111151/1 | INSTALLATION KIT/OH-mechanics.1 kit/cab |  | 1 |  | 1
BAY111151/2 | INSTALLATION KIT/OH-mech.1 front plate/B |  | 1 |  | 1
BAY111151/4 | INSTALLATION KIT/OH-mech.back plate 400, |  | 1 |  | 1
BAY111151/6 | INSTALLATION KIT/OH-mech.side plate,400 |  | 1 |  | 1
BAY111501/4 | INSTALLATION KIT/BACK COVER,DOOR Single | 1 | 1 |  | 2
BFD101131/2 | EQUIPPED MAGAZINE/R 6672 DC Unit | 1 |  |  | 1
BKV301216/156 | FAN/Axial fan, 48 VDC, 52 W, 171.5 x 50. | 1 |  | 4 | 5
BKV301216/90 | FAN/Diagonal fan 48VDC 0,9A 171,5 x 50.8 |  |  | 1 | 1
BML901373/2 | POWER SUPPLY/AC/DC -54V 100W, Portable | 2 |  |  | 2
E15V90P3201 | QUADPLEXER LHHH |  | 3 |  | 3
ECM-00-KX02A(3) | AISG Cont Cable,3m,2 x 8pin conn,1M+1F | 310 | 174 | 86 | 570
ECM-0709EWEW65XX02 | Triband L900/H1800/2100/2600 65°18dBi | 1 |  |  | 1
ECM-0991253228 | 12V AGM 150AH battery | 275 | 166 | 40 | 481
ECM-53K1D7C07N1 | CONNECTOR N(F) FOR 1 5/8""CABLE | 18 |  |  | 18
ECM-60K1CAC05B1 | CONNECTOR 7-16 DIN (F) FOR 7/8"" CABLE | 2736 | 23 | 130 | 2889
ECM-60K1D7C07B1 | 7/16 Connector (F)1 5/8""Aluminium feeder |  | 56 | 38 | 94
ECM-60S1C7C08N1 | CONN 7-16 DIN(M) STRGT FR 1/2"" SuperFlex | 1368 | 973 | 322 | 2663
ECM-64S1C7-C08N1 | 4.3-10 male-1/2"" superflex Straight plug |  | 310 | 94 | 404
ECM-ANTBRKT3MT | antenna bracket-2 flexi arm(76mmx3m)boom | 323 | 112 | 107 | 542
ECM-CB-4-GDWEDF08G | Quadplexer with DC bypass | 78 | 33 | 7 | 118
ECM-CGT12-125X | 12V GEL 125AH Battery | 49 |  |  | 49
ECM-DD300R-05A-B-S | 1U PDU con. of DC bre. 1x16A,6x25A,3x30A |  | 5 | 7 | 12
ECM-ESAA150ACB010 | INDOOR RECTIFIER 2.9 kWa | 2 |  |  | 2
ECM-ESAA150BCBA01 | Indoor power system- 2300W - ESAA150BCBA | 4 | 5 | 3 | 12
ECM-ESOA300ACB010 | Outdoor power system - 2900W-ESOA300ACBD | 7 | 1 |  | 8
ECM-ESOA300BCBD01 | ECM-ESOA300BCBD01 |  | 8 |  | 8
ECM-ESR4856CGA | Rectifier2.9kWESR48/56BC-G- | 40 |  |  | 40
ECM-EXTRM-10070H | SFP 10/100/1000BASE-T , CAT5 cable 100m | 19 |  |  | 19
ECM-G7W8W8W8W8X65V | Penta-Band 5XPol, 694-960/4X1710-2690 MH |  | 1 |  | 1
ECM-HM-3-7F-DF-02 | 698-2700MHz, 3dB Hybrid | 2 |  |  | 2
ECM-L98B755100M | OIL cable 100m (RPM 253 3577) | 128 | 9 |  | 137
ECM-L98B-906-20000 | Fiber Optic LCD(RFE)2FG657-LCD(RFE)=20m |  | 2 |  | 2
ECM-LC081133000 | JUMPER DIN MALE DIN MALE - 3 meters | 3378 | 523 | 267 | 4168
ECM-LC081135000 | JUMPER DIN MALE DIN MALE - 5 meters | 303 |  |  | 303
ECM-LC08-475-3000 | 4.3-10 maleDIN male,3m1/2""superflex jump | 1346 | 410 | 573 | 2329
ECM-LC08-475-5000 | 4.3-10 male-DINmale,5M 1/2’ SFLEX jumper |  |  | 18 | 18
ECM-LM103-074 | 32A DC Circ Breaker - MG 32A 4.5kA MCB |  |  | 10 | 10
ECM-LM103-078 | 25A DC CIRCUIT BREAKER |  |  | 54 | 54
ECM-LT10025151 | X-polar Bracket with Boom |  |  | 4 | 4
ECM-LTTBABS2838 | Fiber Overlength box | 711 | 610 | 553 | 1874
ECM-OD14-065R18J-G | QUADBAND HHHH-COMBA |  | 30 |  | 30
ECM-ODI4-065R18J-G | QB,Xp,4x1710-2690MHz,65,17.8/17.3 dBi,RE |  |  | 6 | 6
ECM-ROS-090 | RET CABLE 100M |  |  | 1 | 1
ECM-SL012SPE | Feeder ½"" Cable Superflex |  | 425 | 374 | 799
ECM-SL078RALPE | Feeder Cable 7/8"" Aluminium | 96 | 227 | 100 | 423
ECM-SL158RAPE | Feeder Cable 1 5/8"" Aluminium | 324 | 3050 | 3056 | 6430
ECM-SLGK004C05060 | Grounding Kit for 7/8"" feeder cable | 1286 | 49 | 130 | 1465
ECM-SLGK004C07060 | Grounding Kit for 1 5/8"" feeder cable | 43 |  | 221 | 264
FAB1021639/01 | SALES OBJECT/1/4"" RF Cable 300m drum | 3300 |  | 840 | 4140
KDU127170/2 | PROCESSOR UNIT/ESC 02 01; Ericsson Site, | 8 |  |  | 8
KDU127174/3 | PROCESSOR UNIT/DUW 31 01;Digital Unit | 1 |  |  | 1
KDU137624/31 | PROCESSOR UNIT/DUS 30 01;Digital Unit |  | 2 | 15 | 17
KDU137739/1 | PROCESSOR UNIT/TCU 02 01;Transport Conne | 1 | 3 |  | 4
KDU137925/31 | PROCESSOR UNIT/Baseband 5216; Digital Un | 9 | 10 | 3 | 22
KDU137925/41 | PROCESSOR UNIT/Baseband 5212; Digital Un | 112 | 53 | 46 | 211
KDU137949/1 | PROCESSOR UNIT/Baseband R503; Auxiliary | 2 |  |  | 2
KEB55002/1 | DETECTOR/Door alarm, Megnetic contact wi | 8 |  |  | 8
KET10951/1 | TEMPERATURE SENSOR/Temp sensor - RJ11 | 15 |  |  | 15
KET10959/1 | SENSOR/Fuel sensor | 7 |  |  | 7
KFE1011162/2 | FILTER UNIT/PFU 02 01; Power Filter |  |  | 1 | 1
KRC115032/2 | TRANSCEIVER/RIU (RET Interface Unit) | 104 | 20 | 2 | 126
KRC115108/1 | TRANSCEIVER/RMU 4.3-10 INT CABLE | 42 |  |  | 42
KRC161262/2 | TRANSCEIVER/RRUS 12 B8;Radio Unit, Type | 2 |  |  | 2
KRC161428/1 | TRANSCEIVER/Radio 2217 B7;Radio Unit | 43 | 18 | 16 | 77
KRC161466/2 | TRANSCEIVER/RRUS 13 B1;Radio Unit, Type | 9 | 32 |  | 41
KRC161469/2 | TRANSCEIVER/RRUS 13 B3;Radio Unit | 12 | 6 | 1 | 19
KRC161473/2 | TRANSCEIVER/RRUS 13 B7;Radio Unit, Type | 2 |  |  | 2
KRC161488/1 | TRANSCEIVER/Radio 2203 B3;Radio Unit | 4 |  |  | 4
KRC161495/1 | TRANSCEIVER/Radio 4415 B7 | 15 | 6 | 10 | 31
KRC161548/1 | TRANSCEIVER/Radio 2217 B8;Radio Unit |  |  | 26 | 26
KRC161609/2 | TRANSCEIVER/Radio 2205 B46 full band | 3 |  |  | 3
KRC161619/1 | TRANSCEIVER/Radio 2219 B3;Radio Unit | 60 | 95 | 93 | 248
KRC161622/1 | TRANSCEIVER/Radio 2219 B1;Radio Unit | 62 | 4 | 8 | 74
KRC161637/1 | TRANSCEIVER/Radio 4415 B3;Radio Unit | 120 | 46 | 7 | 173
KRC161670/1 | TRANSCEIVER/Radio 2219 B8;Radio Unit | 30 | 111 | 25 | 166
KRD901060/82 | TRANSCEIVER/RBS 6402 | 2 |  |  | 2
KRE1012182/1 | ANTENNA/GPS Active Antenna | 1 |  | 2 | 3
KRF102301/10 | FILTER UNIT/Diplex 698-2200+B7/B41 (8-4) | 43 |  | 1 | 44
KRY12168/1 | ACCESSORIES/Kathrein 3GPP/AISG 2.0 RET u |  |  | 3 | 3
KRY901345/2 | Outdoor Directional PB Antenna-RCU | 1 |  |  | 1
KRY901369/2 | ACCESSORIES/Support 6504;Dual DC FAN Sup | 2 |  |  | 2
MB-4W8X33V-00 | TWINBEAM HIGHBAND 8 PORT | 70 |  |  | 70
NCD90145/1 | CONNECTION BOX/Vent Box | 8 |  |  | 8
NCD90156/1 | MODULE/GPS 03 01; GPS Receiver Unit | 1 |  | 2 | 3
NFD30234/08 | OVERVOLTAGE ARRESTER/OVP-ALM 8 | 8 |  |  | 8
NGC90145 | SURGE ARRESTOR/Surge Arrestor | 1 |  | 2 | 3
NGT21104/6 | EARTHING SET/dia 7.6mm Earthing Kit | 8 |  |  | 8
NGT90128/1 | EARTHING SET/1/4"" grounding kit, Alu and |  |  | 2 | 2
NTB1010201/1 | QUANTITY PACKAGE/Cable Bushing | 7 |  |  | 7
NTB1010271/2 | QUANTITY PACKAGE/DCDU 1U Con cables | 2 |  |  | 2
NTB101242/1 | QUANTITY PACKAGE/SAU kit, DF-OVP V3, 10m |  | 8 |  | 8
NTB101242/2 | QUANTITY PACKAGE/OVP kit, 8 Ext Alarm fo |  | 18 |  | 18
NTM1011856/5 | MOUNTING SET/Cabling Brackets/Mtg. Kit 1 | 1 |  |  | 1
NTM1012589/1 | SET OF MATERIALS/6601 subrack kit v2,-48 | 197 | 107 | 51 | 355
NTM2012426 | SEALING SET/Sealing of Connectors,Outdoo | 6 |  | 3 | 9
NTM2014090/2 | SET OF MATERIALS/External Alarm Interfac | 147 | 68 | 42 | 257
NTM203219/10 | SET OF MATERIALS/Clamp Kit 7,6 mm 10 pcs | 4 |  | 4 | 8
NTM503019 | SET OF MATERIALS/DIN rail for 19 | 7 |  |  | 7
NTM50326/92 | SET OF MATERIALS/For "Raised floor" | 1 |  |  | 1
RASO-ANT-0011 | RET Cable 3m | 213 | 140 | 76 | 429
RASO-ANT-0012 | RET Cable 5m | 101 | 2 |  | 103
RASO-ANT-0014 | XXXXPol,2x(694-960)/2x(1710-2690)MHz,QB | 125 | 14 | 14 | 153
RASO-ANT-0015 | XXXXPol,694-960/3x(1710-2690)MHz QB |  |  | 18 | 18
RASO-ANT-0017 | XXPol,2 x 1710-2690 MHz Dual Ultra-WB |  | 21 |  | 21
RASO-ANT-0021 | XXXPol,3x1710-2690 MHz Triple Ultra-WB |  | 13 | 8 | 21
RASO-ANT-0023 | XXXXXPol,2x(694-960)/3x(1710-2690)MHz,PB | 49 | 42 | 44 | 135
RASO-ANT-0024 | Outdoor Directional QB Antenna-RCU |  |  | 13 | 13
RASO-ANT-0055 | QBXpol 698-960+1710-2690 65 16.7/17.9 | 1 |  |  | 1
RASO-ANT-0058 | PB,Xp,698-960+(4x)1710-2690,65°16.7/18/1 |  | 14 | 23 | 37
RASO-ANT-0059 | AISG Control Cable (3 meters) | 20 | 7 |  | 27
RASO-IMT-9025 | OIL cable, single mode, LCD-LCD RFE,100m |  | 1 |  | 1
RASO-IMT-9027 | OIL cable, single mode, LCD - LCD RFE, 150m | 8 | 9 | 1 | 18
RASO-IMT-9031 | OIL cable, single mode, LCD - LCD RFE, 250m |  | 2 |  | 2
RASO-IMT-9033 | OILcable,singlemode,LCD-LCDRFE,300m | 2 |  |  | 2
RASO-IMT-9034 | OIL cable, single mode, LCD - LCD RFE, 30m | 20 | 30 |  | 50
RASO-IMT-9038 | OIL cable, single mode, LCD-LCD RFE, 70m | 1 |  |  | 1
RDH10247/2 | OPTICAL TRANSCEIVER/SFP CPRI & 1000BASE- | 122 | 117 | 2 | 241
RDH10265/2 | OPTICAL TRANSCEIVER/SFP+ SM 10.3Gb/s 1.4 | 810 | 609 | 834 | 2253
RDH901002/1 | OPTICAL TRANSCEIVER/100/1000 TX SSR, SFP | 2 |  |  | 2
RNT44732/02 | CONNECTOR/Circular Power cable connector | 861 | 455 | 133 | 1449
RNY10487/1 | ACCESSORIES/Power Adapter | 663 | 91 | 39 | 793
RPM1136127/1000 | CABLE WITH CONNECTOR/RJ45(8)-RJ45(8) 1m | 41 |  |  | 41
RPM1191647/2 | EARTHING CABLE/16mm2,BK,2m,with 1 lug |  |  | 4 | 4
RPM2530292/100M | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU |  | 65 | 143 | 208
RPM2530292/20M | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU | 21 | 136 | 45 | 202
RPM2530292/5000 | CONNECTION CABLE/2F LC-LC SM RRUS02, RRU | 49 |  |  | 49
RPM2531610/100M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | 321 | 225 | 41 | 587
RPM2531610/20M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | 12 |  |  | 12
RPM2531610/50M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC S | 9 |  |  | 9
RPM2531611/100M | CABLE WITH CONNECTOR/2F LC(FullAXS)-LC M |  | 33 | 30 | 63
RPM2533512/1000 | CABLE WITH CONNECTOR/2F LC-LC SM | 64 | 2 |  | 66
RPM2533512/100M | CABLE WITH CONNECTOR/2F LC-LC SM | 16 | 69 |  | 85
RPM2533512/10M | CABLE WITH CONNECTOR/2F LC-LC SM | 30 | 64 | 60 | 154
RPM2533512/2000 | CABLE WITH CONNECTOR/2F LC-LC SM | 2 |  |  | 2
RPM2533512/5000 | CABLE WITH CONNECTOR/2F LC-LC SM | 42 | 55 | 34 | 131
RPM2533512/50M | CABLE WITH CONNECTOR/2F LC-LC SM | 4 | 19 | 6 | 29
RPM2533513/100M | CABLE WITH CONNECTOR/2F LC-LC MM 50um |  | 132 |  | 132
RPM5132362/20M | CABLE WITH CONNECTOR/2F LC(J-Connector)- | 42 | 40 | 78 | 160
RPM77701/00250 | CABLE WITH CONNECTOR/SIGNAL CABLE | 1 |  |  | 1
RPM77701/00300 | CABLE WITH CONNECTOR/SIGNAL CABLE | 37 |  |  | 37
RPM77701/00750 | CABLE WITH CONNECTOR/SIGNAL CABLE | 12 |  |  | 12
RPM77701/01000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 250 | 23 | 37 | 310
RPM77701/02000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 29 |  |  | 29
RPM777193/00200 | CABLE WITH CONNECTOR/DC POWER CABLE | 17 | 29 | 54 | 100
RPM777193/01300 | CABLE WITH CONNECTOR/DC POWER CABLE | 1 |  |  | 1
RPM777211/01500 | CABLE WITH CONNECTOR/SIGNAL CABLE | 13 |  |  | 13
RPM777263/01000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 2 |  |  | 2
RPM777263/01800 | CABLE WITH CONNECTOR/SIGNAL CABLE | 6 |  |  | 6
RPM777274/01800 | CABLE WITH CONNECTOR/SIGNAL CABLE | 126 |  |  | 126
RPM777279/01000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 4 |  |  | 4
RPM777291/02000 | CABLE WITH CONNECTOR/EARTH CABLE | 631 | 49 | 62 | 742
RPM777298/20000 | CABLE WITH CONNECTOR/DC POWER CABLE | 4 |  |  | 4
RPM777341/00300 | CABLE WITH CONNECTOR/SIGNAL CABLE | 6 |  |  | 6
RPM777381/02000 | CABLE WITH CONNECTOR/SIGNAL CABLE |  |  | 4 | 4
RPM777405/00700 | CABLE WITH CONNECTOR/SIGNAL AND POWER CA | 10 |  |  | 10
RPM777441/03000 | CABLE WITH CONNECTOR/POWER CABLE |  | 4 |  | 4
RPM777442/03000 | CABLE WITH CONNECTOR/POWER CABLE |  | 4 |  | 4
RPM777526/01800 | CABLE WITH CONNECTOR/POWER CABLE | 2 |  |  | 2
RPM777528/01000 | CABLE WITH CONNECTOR/POWER CABLE | 2 |  |  | 2
RPM777554/00500 | CABLE WITH CONNECTOR/POWER CABLE | 40 |  |  | 40
RPM777554/15000 | CABLE WITH CONNECTOR/POWER CABLE | 1 |  |  | 1
RPM777555/05000 | CABLE WITH CONNECTOR/POWER AND SIGNAL CA | 32 |  |  | 32
RPM919619/10000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 545 | 7 | 27 | 579
RPM919665/02400 | COAXIAL CABLE/SMA (m)-SMA (m) outdoor | 18 |  |  | 18
RPM919750/20M | COAXIAL CABLE/Coaxial Cable | 1 |  |  | 1
RPM919750/30M | COAXIAL CABLE/Coaxial Cable | 2 |  |  | 2
RPT899271/1 | CONNECTOR/Andrew, 1/4"" N-Connector (m) |  |  | 4 | 4
RYT921612/1 | MICROCIRCUIT/SFP GB-TX¿ RJ45 SGMII Ether | 6 |  |  | 6
SDF107236/001 | COVER/COVER for Outdoor application (sha | 37 |  |  | 37
SEF901304/1 | BRACKET/RAIL BRACKET | 908 | 344 | 330 | 1582
SEF901305/0180 | BRACKET/RAIL | 966 | 324 | 288 | 1578
SET10306 | CABLE CLAMP/CABLE CLAMP B=2,5 L=142 NATU | 7 |  |  | 7
SG158-06B2A | SureGround Grndg Kit 1 5/8in coax 0.6M |  |  | 4 | 4
S-WAVE-ACU-002-DV6 | Rosenberger RET |  | 32 |  | 32
S-WAVE-ACU-002-DV8 | Rosenberger RET |  |  | 1 | 1
S-WAVE-ACU-003-DV8 | Rosenberger RET |  |  | 6 | 6
SXA1060216/15 | FLOOR PANEL/EQ 2xBYB501 600x800, 4 cut-o | 1 |  |  | 1
SXA120119/1 | BRACKET/Down tilt kit |  |  | 1 | 1
SXA1342193/2 | MECHANICAL COMPONENT/Dummy 31 (Plastic v | 4 | 22 | 47 | 73
SXA210404/1 | CABLE SHELF/Shelf H=25 mm, | 17 |  |  | 17
SXK1091931/1 | ASSEMBLED PARTS/GPS Mount, Steel | 1 |  | 2 | 3
SXK111539/1 | MOUNTING SET/RACK SCREW KIT | 198 | 199 | 141 | 538
SXK1250245/1 | ASSEMBLED PARTS/MOUNTING KIT (MK mast br | 39 | 24 | 62 | 125
SXK1252540/1 | ASSEMBLED PARTS/MOUNTING KIT | 256 | 336 | 291 | 883
TFL104510/08 | CABLE/S1Z1-K 1x50 MM2 (1 AWG), UL 90 Deg | 2 |  |  | 2
TFL281324 | INSTALLATION CABLE/HALOGENFREE,2X6,600V, | 1 |  |  | 1
TFL281326 | INSTALLATION CABLE/HALOGENFREE,2X16,600V | 1 |  |  | 1
TFL492324/500M | POWER CABLE/2x6 mm2;UL;LSOH;Alu+Cu-scree | 428 | 161 |  | 589
TFL492325/100M | POWER CABLE/2x10 mm2;UL;LSOH;Alu+Cu-scre |  | 200 |  | 200
TFL492325/300M | POWER CABLE/2x10 mm2;UL;LSOH;Alu+Cu-scre | 100003 | 13189 | 5972 | 119164
TFL90117/24 | CABLE/2x6mm2 (10AWG) 600V 90C UL 10 m co | 27 |  |  | 27
TPM1010027/15M | CABLE/TFL 252015/16 15m SPOOLED | 171 | 72 | 36 | 279
TPM1010030/30M | CABLE/TFL 252 017/002¿¿ 30m¿ outdoor¿ SP | 8 |  |  | 8
TSR432151/10M | CONNECTION CABLE/Signal Cable | 33 |  |  | 33
TSR432151/15M | CONNECTION CABLE/Signal Cable | 2 |  |  | 2
TSR432151/2000 | CONNECTION CABLE/Signal Cable | 20 |  |  | 20
TSR491603/10M | CABLE WITH CONNECTOR/SIGNAL CABLE | 1 |  |  | 1
TSR491603/60M | CABLE WITH CONNECTOR/SIGNAL CABLE | 2 |  |  | 2
TSR491628/5000 | CABLE WITH CONNECTOR/SIGNAL CABLE |  | 1 |  | 1
TSR491641/5000 | CABLE WITH CONNECTOR/SIGNAL CABLE | 1 | 1 |  | 2
TSR49336/3000 | CABLE WITH CONNECTOR/POWER CABLE | 100 |  |  | 100
TSR49345/3000 | CABLE WITH CONNECTOR/POWER CABLE |  | 2 |  | 2
TSR951338/1500 | CONNECTION CABLE/Jumper N(m)-SMA(m) 1.5m | 1 |  |  | 1
TSR951345/2 | CONNECTION CABLE/Jumper N(m)-N(m) 10m | 1 |  |  | 1
TSR951357/1500 | CONNECTION CABLE/Jumper N(m)-SMA(m) 1.5m |  |  | 2 | 2
TSR951367/3 | JUMPER CABLE/Rosenberger 1/2"" jumper cab | 36 |  |  | 36
(blank) | (blank)
Grand Total |  | 127145 | 25308 | 17149 | 169602